Discussion Note

Network Optimisation and Middle-Mile Synergy between V-Trans and V-Xpress

| Document type | Internal discussion note |
| --- | --- |
| Subject | Network optimisation and synergy between V-Trans and V-Xpress |
| Scope | Middle-mile hub–branch structure, routing and feeder alignment |
| Out of scope | Need-based scheduling and spot vehicle engagement |

1. Purpose

This note sets out a structured approach to evaluate and unlock network optimisation and middle-mile synergy between V-Trans and V-Xpress—two operating verticals under the same legal entity. The intent is to improve asset utilisation, reduce duplication of hubs/branches and routes, and strengthen service economics without compromising the distinct commercial propositions of either business.

2. Background

V-Trans and V-Xpress operate under one legal entity but as distinct business verticals, each serving clients with transportation solutions of a different character.

| Dimension | V-Trans | V-Xpress |
| --- | --- | --- |
| Business model | Conventional part-truck-load (PTL) operator | National express logistics provider |
| Geographic strength | Strongest in West; followed by South and North | National express footprint |
| Geographic weakness | East is the weakest zone | East is also the weakest zone |
| Client & service proposition | Differentiated on pricing, shipment profile, service quality and time sensitivity | Differentiated on pricing, shipment profile, service quality and time sensitivity |
| Middle-mile design | Independent hub–branch and line-haul construct | Independent hub–branch and line-haul construct |

While client propositions differ in pricing, shipment profile, service quality and time sensitivity, the middle-mile operating models are entirely distinct. At the same time, both businesses largely cover similar geographic territories. Differences are often limited to:

choice of hub cities in selected markets; and

within the same city, different site locations rather than different catchments.

This overlap creates a clear opportunity for structural synergy, provided integration respects business-model and site-level constraints.

3. Objective

The organisation seeks to:

Optimise the network and routing of both businesses; and

Evaluate and capture synergy in the middle-mile network of V-Trans and V-Xpress.

Explicitly excluded from this project: need-based scheduling and spot engagement. The focus is on the structural network—hubs, branches, fixed connections and feeder design—not tactical daily vehicle hiring.

4. Problem framing

The mandate comprises two related but non-identical problems:

| Problem | Description |
| --- | --- |
| A. Network optimisation | Redesigning hubs, branches, line-haul and feeder routes for efficiency, cost and service under projected combined (and residual standalone) loads |
| B. Synergy evaluation | Identifying where co-location, shared connections and shared feeder design create value without damaging either vertical’s service promise |

As of today, the two networks run independently. A full merger of middle-mile operations would yield benefits in principle; however, bringing both businesses onto the same physical sites and connections may be constrained by:

business-model requirements (PTL vs express; handling, cut-offs, SLA);

site suitability (space, access, compliance, landlord terms); and

connection / lane design differences.

Consequently, network and route optimisation cannot be run credibly in isolation. Meaningful optimisation becomes possible only after hub and branch footprints are synchronised and aligned wherever feasible. Non-aligned nodes must be treated as residual standalone capacity in the final design.

5. Guiding principles

Sequence before scale — Align physical nodes first; optimise combined routes thereafter.

Synergy with selectivity — Co-locate and combine only where operationally and commercially justified.

Preserve service identity — Express and PTL propositions must not be diluted by forced integration.

Evidence before relocation — Decisions on shifting sites must rest on load, connection and catchment analysis.

Exclude tactical noise — Spot and ad-hoc scheduling remain outside the optimisation scope.

Phased execution — Prefer staged, reversible moves over a big-bang network redesign.

6. Recommended phased approach

All project activities cannot—and should not—run concurrently. A step-wise programme is proposed as follows.

Phase 1 — Hub and branch alignment assessment

Objective: Establish a fact base of current locations, loads and connections for both entities, and identify where co-location / alignment is feasible.

Key activities

Map all hubs and branches of V-Trans and V-Xpress independently (city, site, role, capacity).

Map loads and middle-mile connections for each node.

Overlay both networks to identify:

- Low-hanging opportunities — same city / nearby sites; quick co-location possible;

- Medium-term opportunities — alignment possible after lease, layout or process changes;

- Non-doable locations — constrained by business model, site, or connection design.

Where relevant, identify preferred branch locations using centre-of-gravity analysis of pick-up and delivery volumes.

Output: Alignment opportunity matrix (doable / deferred / not feasible), with indicative benefit and constraint notes by location.

Phase 2 — Hub and branch alignment execution (interim window)

Objective: Physically align selected sites—especially short-term, low-hanging opportunities—before a full network optimisation is run.

Key activities

Execute co-location / site shifts for prioritised locations.

Stabilise operations at aligned sites (cut-offs, handling norms, space allocation between PTL and express where shared).

Maintain a live register of aligned vs non-aligned nodes.

Indicative duration: approximately 3 to 6 months, depending on lease cycles and execution complexity.

Rationale: Running a combined network model on a footprint that is still in flux will produce unstable and non-implementable recommendations. An intermediate alignment window improves the quality of the subsequent optimisation.

Phase 3 — Combined middle-mile network optimisation

Objective: Optimise the middle-mile network on the combined load of both businesses, once doable and non-doable hub alignments are clearly visible.

Key activities

Build a combined demand and connection view for aligned geography.

Optimise hub roles, line-haul routes and frequencies for the joint load.

Treat non-aligned V-Xpress (and/or V-Trans) nodes separately in the final design so that residual standalone requirements are not forced into an invalid combined solution.

Stress-test service implications (transit time, cut-offs, handovers) for both verticals.

Output: Recommended middle-mile network design—combined where aligned; standalone overlays where not.

Phase 4 — Feeder route alignment and optimisation

Objective: As the final structural step, align and optimise feeder routes feeding the (re)designed hub–branch network.

Key activities

Redesign feeder circuits around aligned hubs/branches.

Eliminate duplicate feeder coverage where catchments overlap.

Confirm first-mile / last-mile interface impacts on service quality for both businesses.

Output: Feeder plan consistent with the optimised middle-mile backbone.

7. High-level roadmap

| Stage | Focus | Outcome |
| --- | --- | --- |
| 1. Assess | Independent mapping + co-location opportunity matrix | Clear list of doable / deferred / non-doable alignments |
| 2. Align | 3–6 month execution of short-term site alignments | Stabilised joint footprint for optimisation |
| 3. Optimise | Combined middle-mile network design; residual nodes handled separately | Implementable joint + standalone network blueprint |
| 4. Extend | Feeder route alignment and optimisation | End-to-end structural network synergy |

8. Proposed methodology and tools

| Option | Suitability for this programme |
| --- | --- |
| Network design tools (e.g. Log-hub, LLamasoft / Coupa, IBM ILOG-class solvers) | Useful for refinement at a later stage once the aligned footprint and data model are stable |
| Structured manual / Excel-based analysis | Recommended for the first implementation cycle, given current dual-network complexity, co-location constraints and the need for judgement on business-model fit |

Recommendation: Proceed with a manual, analytically structured approach for Phase 1–3 in the first wave. Tool-based optimisation may be explored subsequently to improve precision and scenario testing once alignment decisions and data quality support a model-driven exercise.

9. Data and analytical requirements (indicative)

To execute the approach, the programme will require (at minimum):

Hub/branch master with city, site coordinates, role, capacity and lease/ownership status (both entities);

Middle-mile lane and connection matrix (origin–destination, frequency, vehicle type, utilisation);

Volume and shipment-profile data by node and lane (PTL vs express);

Service parameters (cut-offs, target transit, handling constraints);

Cost elements relevant to line-haul, hub handling and facility duplication;

City-level pick-up/delivery density for centre-of-gravity branch assessment.

10. Expected benefits (directional)

Subject to validation in Phases 1–3, the programme is expected to enable:

reduction in duplicate facility and connection cost in overlapping cities;

improved middle-mile vehicle utilisation on shared corridors;

clearer hub roles and fewer fragmented line-haul runs;

stronger East-zone design options through joint volume visibility (a shared weakness today);

a cleaner base for future tool-based optimisation.

Benefits should be quantified location-by-location during the alignment assessment and reconfirmed after the combined optimisation.

11. Risks and constraints to manage

| Risk / constraint | Mitigation |
| --- | --- |
| Forced co-location harms express or PTL service identity | Apply selective synergy; retain standalone design where needed |
| Lease and site constraints delay alignment | Prioritise low-hanging sites; park non-doables explicitly |
| Optimising before alignment produces non-implementable plans | Enforce the Phase 1 → 2 → 3 sequence |
| Incomplete or inconsistent dual-network data | Invest in mapping quality before optimisation |
| Scope creep into spot / daily scheduling | Keep tactical hiring outside project boundaries |

12. Decision points for leadership

Leadership guidance is sought on the following:

Acceptance of the phased sequence (assess → align → optimise → feeder), rather than a single-step joint optimisation.

Mandate to execute short-term co-locations during the 3–6 month interim window where the opportunity matrix supports it.

Confirmation that spot/scheduling optimisation remains out of scope for this project.

Agreement to commence with a manual analytical methodology, with tool-based enhancement as a subsequent phase.

Nomination of a joint steering group (Operations / Network from both verticals + Finance) to approve doable / non-doable classifications.

13. Conclusion

V-Trans and V-Xpress share geography more than they share middle-mile design. That overlap is the opportunity; the difference in business model is the constraint. The correct response is not an immediate full merger of networks, nor independent optimisation of two siloed systems. It is a disciplined, phased programme: align hubs and branches where feasible, execute the practicable co-locations, then optimise the combined middle-mile—and finally feeders—while explicitly carrying non-aligned nodes as residual design.

This sequence maximises synergy where it is real, protects service propositions where integration is not viable, and produces a network plan that can actually be implemented.

End of discussion note